## Overview
Crowdfunding Overview: This document is the 'ideal world' approach to your Crowdfunder campaign. Do not panic, if you don’t manage everything outlined here. Do what you can, with what you have. Use the skills of your band members and friends to help you with social posts, sending emails, contacting the press etc
MARKETING PLAN This is the timeline for your crowdfunding campaign. It outlines the activities that should take place before and after your launch date to get you to your target. Preparation is key to a successful crowdfunder campaign. Good crowdfunding requires organisation and this plan will help you to prioritise your time, cover all of the necessary bases and get the best out of your network. We’ve put together a template that you can use to start you off.
SUPPORTERS This is where you can list partner organisations, journalists, VIPs, influencers, marketing channels, businesses, celebrities etc who may be able to help you promote your campaign. Start with the organisations or individuals who you have closest connections with (usually smaller/local), and then list organisations or individuals you could contact (usually regional/national) to expand your campaign reach.
SOCIAL MEDIA POSTING PLAN - Use this sheet to help map out the content you create for your social media channels. - Remember to tag in relevant contacts; influencers, fundraisers, celebrities, media, community groups etc. Content should appeal to particular audiences and encourage social sharing. - Use the campaign imagery provided but you can also use many of the free online design tools eg Pablo or Canva to quickly design and create your own customised images. - Don't forget the powerful nature of video - and ask your contacts to create their own to show their support. - If you can onboard a celebrity to support the project by asking them to change the link in their Instagram bio to your crowdfunder project page link and then for them to post content driving to it, that can be powerful too, or perhaps to pin a tweet. - Find relevant social media groups to join and post in - especially Facebook and Nextdoor - Don't forget to use the hashtag #BrassBandsAtChristmas in every post - hashtags are important because they help people find you and also if everyone uses it, it may start trending which means a much bigger reach!
EMAIL EXAMPLE - Tailor this email for your own band and fundraising ambitions. - It mentions fundraisers, which is relevant to those of you who choose to have 'Multiplier' mode switched on. (This enables fundraisers to create pages and for them to sell any rewards you have on your page. If you would like this mode turned on, please contact us). - You don't need to send the same email to everyone - you can target different audiences with different asks, or you can let your supporters decide how they would like to support you - ie, purchase a reward, enter a prize draw, donate or fundraise. - Also customise the emails you use to approach businesses for match funding or to obtain rewards and those you use to approach the press to sell in your story.
FUNDRAISER LIST This is a list of potential fundraisers, their contact details and how much they're likely to raise. You can keep notes on who you’ve contacted and what they've agreed to. Do check in with your fundraisers regularly to give them support and encouragement. Remember, they can sell your rewards for you, so tell make sure you highlight this to them as it will really help them to reach their individual targets, making them more likely to take part.
PRESS RELEASE Brass Bands England are providing a press release about the overall campaign that you can tweak and use to obtain coverage for your campaign too. You can prepare for this by getting in touch with members of the press that you know (and reach out to those you don't!) to talk to them about the campaign in advance and let them know that you plan to send over a press release.

## Marketing Plan
MARKETING PLAN TEMPLATE
A marketing plan is a timeline of your crowdfunding campaign and the activities that should take place before and after your launch date to get you to your target. Preparation is an important element to a successful crowdfunder campaign. Good crowdfunding requires organisation and a marketing plan will help you to prioritise your time, cover all of the necessary bases and get the best out of your network. Remember to enlist help and delegate responsibilities. We’ve put together a template that you can use to start you off.
PLANNING STAGE (IDENTIFYING YOUR CROWD) | Theme | Activity | Channel | Audience | Key Message | Completed
| NETWORK MAP | Create a list of potential local, relevant and national supporters in the supporters tab. (e.g. audiences, parents of young players, business partnerships) | - | - |  | Not Complete
| INFLUENCERS & SUPER-BACKERS | Create a list of key influencers and 'super-backers' relevant to your project, both local and national (remember start local and work your way out). Use supporters tab. | - | Key influencers that will have a big impact on your project | Ask them to pledge early and / or donate rewards or prizes in return for a shout out | Not Complete
| AREAS OF INTEREST | Split up your supporters into the different areas of interest to enable content to be targeted appropriately | - | Groups of people interested in a particular element of your project so you can create targeted messaging that appeals |  | Not Complete
| RELEVANT EVENTS | Research and contact any relevant events you can attend or speak at about your project (in person or online) | - |  |  | Not Complete
PLANNING STAGE (NURTURING YOUR CROWD) | Theme | Activity | Channel | Audience | Key Messages | Completed
| EXISTING SUPPORTERS | Contact existing supporters; Offer them early bird access to your Rewards to ensure some early donations on the page. Keep a note of any who accept. | Email, phone | Existing supporters / customers | Start telling your Story - why are you fundraising, and why now? Why is your band important to the players and to the wider community? Why are brass bands in general an important part of the Christmas experience? What emotional hooks have you got that will make people want to donate? | Not Complete
| SOCIAL MEDIA | Get active and warm up your Facebook, Twitter and Instagram followers before launch. Encourage them to invite friends to follow you so they can hear all about the upcoming campaign. | Facebook, Instagram, Twitter | - |  | Not Complete
| RELEVANT GROUPS | Start getting active in relevant groups on Facebook and LinkedIn; Be engaging, tell your story. | Facebook, LinkedIn | Relevant audiences online |  | Not Complete
| LOCAL PEOPLE | Get networking and collect contacts. Email groups you'd like to engage with the campaign, attend meetings and events. Or use online tools to network, such as LinkedIn. | Networking - on and offline | Local community |  | Not Complete
| UPDATE WEBSITE | If you have time, create a landing page on your website with a 'coming soon' message and an opt-in check box (opt in to further communications) Offer something interesting in return for their email address. | Online / Email | Existing supporters / customers |  | Not Complete
| ADDITIONAL RESOURCES | *CONTINUE TO NURTURE YOUR CROWD THROUGH THE CREATING STAGE OF YOUR CROWDFUNDER PROJECT, CLICK HERE TO SEE GUIDES FOR MORE DETAILS
COUNT DOWN TO LAUNCH | Theme | Activity | Channel | Audience | Key Message | Completed
| QR CODES | Download your personal QR code from the dashboard in your Crowdfunder page. | Offline - Flyers, Posters, Programmes, Tickets
| SAVE THE DATE | Create a Facebook event and invite everyone in your network to save the launch date in the diary Start building excitement e.g send out messages, create poster(card)s with the launch date and QR code on | Facebook / Printed Flyers / QR code |  |  | Not Complete
| PREPARE IMAGES | Create plenty of content before you go live e.g., photos & video of people, places and events. See posting plan for ideas. Having bright, bold images available makes creating posters, flyers and social media posts much easier and effective | You can use Pablo or Canva | - |  | Not Complete
| REWARDS AND PRIZES | If you want to offer rewards in return for donations or run a prize draw, start thinking about what you will offer. Rewards = you sell each reward at different price points in return for a donation (eg £5 gets you a pen and a notepad, £500 gets you a private performance) up to a certain amount. You can also add Rewards at any time during your fundraising. Prize draw = everyone buys a ticket at same price to be in with the same chance of winning a range of prizes from pens to private performances. You need terms and conditions and a no-purchase necessary route to run a prize draw https://www.crowdfunder.co.uk/programmes/prize-draw-guidelines | Your project page |  | Local businesses, super backers and celebrities | Not Complete
| EMAIL SIGNATURE | Write a short, compelling statement about your fundraiser with a link to your project page and distribute to everyone to attach to their email signatures. You can even design an image instead of text | Use Pablo or Canva to help | Band members, existing supporters (individual and business) | Help us raise more funds by adding the link to your email signature | Not Complete
| LINE UP THE FIRST 10% OF PLEDGES. CONSIDER FUNDRAISERS | Aim to get the first 10% lined up before you go live, by contacting those closest to you and asking them to pledge on the campaign in the first few hours of going live. If they are super engaged supporters, see if they will make a fundraiser page which will contribute to your overall target. | Phone |  |  | Not Complete
| GET ON THE PHONE | Get in contact with everyone you've identified / nurtured during the planning stage reminding them of your launch date | Phone (keep it personal and don't cold call people you don't actually know) |  |  | Not Complete
| LAUNCH PARTY | Plan a launch party/ performance for day 1 to get everyone excited about your campaign. Invite all the key groups identified in your network map; Make it exciting and encourage people to pledge there and then - this is where QR codes come in handy! |  |  |  | Not Complete
LAUNCH WEEK | Theme | Activity | Channel | Audience | Key Message | Completed
WEEK 1 | LAUNCH DAY - EMAILS | Message personal contacts reminding them to pledge on day 1. Be personal, be direct. | Phone / Personal Email / SMS |  |  | Not Complete
| Always include a 'call to action' to your Crowdfunder page in all your communications. Also remember to use the campaign hashtag | Once you have the first 10% on the board send a group email to the email database you've created; Mailchimp is a good tool to do this, you can check click rates, open rates and re-target those who didn't engage 1st time round. | Group Email (Mailchimp) |  |  | Not Complete
|  | Email your list of super-backers / influencers individually reminding them to pledge on the campaign: eg larger backers and local businesses. If they don't reply straight away, follow up with a subtle reminder a few days later name dropping those who have pledged so far. | Email |  |  | Not Complete
| LAUNCH DAY - WHATSAPP | Make sure that any groups (friends and family) that you are members of on WhatsApp are primed and ready to share the link on social media after they have pledged. Ask them to send the link directly to at least 2 people who they think might be interested in your campaign. This is an excellent network building exercise | Group WhatsApp |  |  | Not Complete
| LAUNCH DAY - FACEBOOK | Once you have 10% on the board, announce on Facebook that your project is now open. Share the post in the Facebook Event you created with the launch date. Boost the post, targeting the relevant audience - a little spend on Facebook can go a long way and potential showcase your project to new supporters. | Facebook |  |  | Not Complete
| LAUNCH DAY - UPDATE WEBSITE | From launch for the duration of your campaign you should divert all traffic to your Crowdfunder. Create a link to your Crowdfunder page. Embed your own unique Crowdfunder widget to your website. Disable any other donate buttons on your website during the campaign. | Own Website |  |  | Not Complete
| LAUNCH DAY - PARTY | As mentioned above. | -
| LAUNCH DAY - OFFLINE | Get out and about; create flyers, post them in the local community, ask local shops/hubs to put them out. Be creative, create a stunt activity eg a flashmob which will grab supporters attention! | Offline - Flyers, Posters - with your QR Code |  |  | Not Complete
| LINE UP PRESS | Wait until you have some momentum before pushing out a press release but start lining up local media / relevant media to contact. (We will be sharing a press release for the overall national campaign you may like to use) | Press |  | We've hit a key milestone eg £1000 raised, or 100 donations | Not Complete
MID-CAMPAIGN | Theme | Activity | Channel | Audience | Key Message | Completed
WEEK 2 | MAINTAIN ACTIVITY ON SOCIALS | Maintain engagement on Social Media. Aim to post x1 a day on Facebook (or Twitter, Instagram, LinkedIn)- see posting plan for content ideas Remember you don't always have to mention your Crowdfunder campaign but do include a 'call to action' link to your CF page | FB, Twitter, Instagram, LinkedIn |  |  | Not Complete
|  | Facebook is the best tool for generating pledges; Twitter is brilliant for generating awareness; LinkedIn is a great place to look for corporate support; Instagram is best suited for businesses with strong visuals. |  |  |  | Not Complete
| REVIEW NETWORK MAP / SUPPORTERS TAB | Get a sense of which activities have been productive and who needs more work. Spend time calling through and messaging the local businesses and those beyond your personal network
| EMAIL - NEWSLETTER | Send out a campaign update in your newsletter; as mentioned above MailChimp is great tool to do this. | Email Newsletter (MailChimp) |  |  | Not Complete
| PRESS - LOCAL NEWS | Contact and share your campaign with local media; local news outlets love publishing stories with local angles, so make the connection clear in your press release. Make sure you send any relevant images, your CF page URL and make sure it's included in the article. | Press Release |  |  | Not Complete
| PRESS - LOCAL RADIO / TV | Line up airtime on local radio; Don’t be disheartened if you don’t get any coverage straight away – be persistent and try pursuing different angles. | Local Radio / TV |  |  | Not Complete
WEEK 3 | MAINTAIN ACTIVITY ON SOCIALS | MID-CAMPAIGN IS AN IMPORTANT TIME TO MAINTAIN MOMENTUM Maintain engagement on Social Media: Continue to post x1 a day on FB (or Twitter, Instagram and LinkedIn); Remember you don't always have to mention your Crowdfunder campaign but do include a 'call to action' link to your CF page | FB, Twitter, Instagram, LinkedIn |  |  | Not Complete
| ORGANISE A MEETING WITH TEAM | Get a date in the diary that works with everyone, review your progress and reflect on what you can do to move things forward | In person, Skype, Zoom, WhatsApp |  | What has worked so far? What hasn't? What we could try and actions for this week
| WEEKLY UPDATES via CROWDFUNDER | Send out weekly updates to your supporters via Crowdfunder; Keep your supporters updated on how the campaign is performing and any ongoing plans etc. | Crowdfunder |  |  | Not Complete
| RELEASE NEW REWARDS | Don't be afraid to hold back rewards and release them mid-campaign to maintain buzz. Also, if rewards sell-out and you can make more available - re-release them with an update via CF and social media. | Crowdfunder / Social Media
| EMAIL - NEWSLETTER | Send out an update of your campaign in a weekly newsletter, as mentioned above MailChimp is great tool to do this. | Email Newsletter (MailChimp)
| PRESS - RELEVANT NATIONAL MEDIA | Contact and share your campaign with relevant media. Now would be a good time (once you have c.50% of your target) to approach more national media that is relevant to your project. Again, make sure you send any relevant images and your CF page URL and make sure it's included in the article. | Press Release ONLINE / OFFLINE |  |  | Not Complete
| BLOGGERS | Contact bloggers relevant to your project and ask them write a piece on your work, with a link to your Crowdfunder project. Bloggers are contacted every day by strangers who only want publicity, without offering much in return. To stand out, think about out how you can help them out – don't rush straight in with your request. |  |  |  | Not Complete
| MID-CAMPAIGN EVENT | Celebrate the halfway point of your campaign |  |  |  | Not Complete
| CHASING | This is an essential part of crowdfunding. Many people will forget to pledge, so it's important to send them a light prompt to do so. The more personal the message the more effective you'll be.
FINAL WEEK | Theme | Activity | Channel | Audience | Key Message | Completed
Week 4 | COUNTDOWN ACTIVITY ON SOCIALS | Line up a countdown of social-posts to go out each day during the final week of your project | FB, Twitter, Instagram, LinkedIn |  |  | Not Complete
| COUNTDOWN UPDATES via CROWDFUNDER | Send out daily updates to your supporters via Crowdfunder | Crowdfunder |  |  | Not Complete
| PAID SOCIAL | Boost one final FB post with a CTA in the final week. | FB |  |  | Not Complete
| END-CAMPAIGN EVENT | Gather everyone for an event an hour before the campaign closes. You can rally for some more pledges from around the room and get to celebrate the moment with your Crowd. | Virtual or in person
| CORPORATE SUPPORT | Continue to contact local businesses who may wish to pledge on your campaign; Be prepared to be flexible to meet their requirements; LinkedIn is a good tool to get corporate pledges but don't be afraid to get on the phone or visit them yourself, be personal - you don't know what you may receive in the final few days! | LinkedIn / Phone / In person |  |  | Not Complete
| INFLUENCERS | Get in touch with your list of influencers thank them for their help and request one last post to their audience | Facebook / Instagram / Twitter |  |  | Not Complete
| PERSONAL NETWORK | Use Facebook or WhatsApp to post on any groups that you are part of and request that everyone shares the link on Facebook with a message to encourage their contacts to pledge | Facebook / WhatsApp |  |  | Not Complete
| CELEBRATE | Don't forget to thank your supporters in helping you get to your total raised. Use the update tab or thank them using their preferred communication channel |  |  |  | Not Complete

## Supporters
SUPPORTER LIST
# | Names of Supporters | Supporter Category (Partners / Business/ Influencer / VIP / Celebrity / Super Backer / Press Contacts / Marketing Channels) | Est. Audience Size | Contact details | Any initial amounts pledged | Notes / What's Been Agreed
1 | X famous musician | Celebrity | 100000 |  | 500 | Will create a video of support and post on their social media. Happy to be quoted in a press release as saying xxxxxx
2 | Name of local business | Business - included in their newsletter and on their social media channels | 10000 |  | Rewards worth £xx | Provided rewards of xxxx (include quantity and when they will be distributed) and offered to share crowdfunder page with their database via a newsletter and in social media posts to help sell the reward they have provided
3 | X journalist | Press | 200000 |  | 50 | Will repost on their own social channels and link to the article on their news website. Will publish your press release in the paper and online
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
| TOTALS |  | 310000 |  | 550

## Fundraiser List
Fundraisers List
# | Fundraiser Name | Likely amount to Fundraise | Contact details (It's useful to include their social media handles to tag in thank you content and also their email address). | Notes.
1 | E.g. John Smith | 150 |  | Planning a sponsored xxxxx
2 |  | 150
3 |  | 150
4 |  | 150
5 |  | 150
6 |  | 150
7 |  | 150
8 |  | 150
9 |  | 150
10 |  | 150
11 |  | 150
12 |  | 150
13 |  | 150
14 |  | 150
15 |  | 150
16 |  | 150
17 |  | 150
18 |  | 150
19 |  | 150
20 |  | 150
21 |  | 150
22 |  | 150
23 |  | 150
24 |  | 150
25 |  | 150
TOTAL |  | 3750

## Social Media
SOCIAL MEDIA POSTING PLAN - TEMPLATE
You can use Pablo or Canva to create social images for your campaign - they will help you format them in the correct dimensions as well! The more people you get sharing your page, the better. Think of celebrities and industry influencers you can get onboard to share content and tag them into content. (If you can verbally ask them to back your campaign in advance then do so and then tag them into your social posts). Reach out to performers with a large following and ask them to create videos or messages of support and post them on their channels
Please tweak content wording and order posts as needed for your individual campaigns - some of these posts will need shortening for Twitter but are fine for Facebook and Instagram. You can also tweak the duration of your campaign to suit your individual needs but the main campaign runs from Nov 17 - Dec 17. Keep an eye on which posts perform best, learn from them and repeat the element that made them successful later in the campaign. Remember to use the hashtag #BrassBandsAtChristmas when posting. Only talk about individuals creating fundraising pages if you have the Multiplier function turned on for your campaign.
Timing | Example of a general social post | URL (Generally this is the link to your crowdfunder page but occasionally you can vary this, e.g. if you want to highlight a fundraisers page instead) | Image/Video | Social Tagging?
17.11.21 | We're live! We’ve launched a @CrowdfunderUK campaign to help us raise funds for our beloved xxxxx Brass Band. Help us keep #BrassBanding a key part of the Christmas experience #BrassBandsAtChristmas |  | Feature campaign image | Facebook: @Crowdfunder Twitter: @CrowdfunderUK Instagram: @ LinkedIn: @Crowdfunder UK
18.11.21 | DAY 2! If you’d like to fundraise for xxxx Brass Band and help us to support #BrassBandsAtChristmas you can create a fundraising page here. Click the 'start fundraising' button to create your page and share it with your friends. You'll be able to sell the rewards we have on our main page via your page too! |  | Image of a fundraiser | tag in any potential fundraisers. Are there any celebrities who you can ask?
19.11.21 | Day 3. LOCAL BUSINESSES! Can you help us to raise funds to support our Brass Band? Please donate to our @CrowdfunderUK campaign here: xxx All shares or mentions are also greatly appreciated! #BrassBandsAtChristmas |  | Campaign image | @ for local businesses
20.11.21 | So proud to announce that Xxxx is supporting our Crowdfunder campaign! Together we are highlighting the importance of #BrassBandsAtChristmas |  | Celeb video or quote | Celebrity / influencer
21.11.21 | Our current top fundraiser is .... who is doing..xxx.. for us! See how you can get involved in the fun and become top of the leader board by clicking here! ........ #BrassBandsAtChristmas |  | Fundraising image | Tag fundraisers
22.11.21 | Check out the great rewards you can purchase to support our #BrassBandsAtChristmas campaign. All funds go towards keeping your local Brass Band going during these tough times. |  | Images relating to your rewards | The companies or individuals who provide the rewards to see if they will share the post.
23.11.21 | Short on fundraising ideas to raise funds to help us to #BrassBandsAtChristmas? Have you thought of xxxx (insert ideas) |  | Someone doing a fun fundraising activity | Fundraisers/ celebrities
24.11.21 | Calling all local community groups, please help us to raise £xxxxx for our brass band #BrassBandsAtChristmas |  | Video clip | community groups
25.11.21 | [insert a relevant stat - members, instruments, performances] Help us raise £xx for our xxxx by sharing this with your colleagues/ friends/ family #BrassBandsAtChristmas |  | Social image on the relevant stat. | Local councillors.
26.11.21 | Thank you so much to @xxxx for your generous donation! Join [insert name] and support us here: [URL] #BrassBandsAtChristmas |  | Thank you image | Tag donor
27.11.21 | Please help us to xxxxx ! Please donate to our campaign or help us fundraise here. So far we've raised £xxx Thank you! #BrassBandsAtChristmas |  | Amount raised so far | Local press / journalists if you’ve raised enough to highlight this to them by then
When PR is obtained | Thanks to xxx local radio for hosting us and helping us promote our campaign to celebrate #BrassBandsAtChristmas |  | Thank you image | Radio station
29.11.21 | Your donation of £xx can do xx for your local brass band. Thank you for your support! #BrassBandsAtChristmas |  | Thank you image | Local businesses
30.11.21 | Is live performance important to you? Looking for a way to help your community? Please share our crowdfunder page with your friends and family. #BrassBandsAtChristmas |  | Image of kids performing | local schools
1.12.21 | Thank you to our current top fundraiser @xxxxx who is doing..xxx.. #BrassBandsAtChristmas | Add link to fundraiser page | Well done / Congratulations image | Tag fundraiser/s
2.12.21 | Do you run a business in xxx area? Are you in a position to help #BrassBandsAtChristmas? Check out our Crowdfunder campaign here. |  | Pic of a business leader | businesses
3.12.21 | A donation of £xx can help us do xxxx. Please support our Crowdfunder campaign here and celebrate the joy of #BrassBandsAtChristmas |  | Campaign infographic | band members to share
4.12.21 | Thanks to @xxxxx for promoting our work! Find our more about our campaign here. Please share and show your support for #BrassBandsAtChristmas |  | Link to any press written | tag PRs
5.12.21 | Woah we're halfway there! 2 weeks left of our Crowdfunder campaign! We've raised £xx from xx fundraisers and xx supporters! Please share and support us in reaching our target! #BrassBandsAtChristmas |  | £XX raised so far | Tag in influencers
6.12.21 | With #Christmas on the way, surprise a loved one with a carol performance outside their home. Available via our Crowdfunder page for only £xx #BrassBandsAtChristmas |  | Carol performance | band members to share
7.12.21 | Thanks to everyone who has helped us raise X% of our target for our Crowdfunding campaign! Keep up the good work you lovely people #BrassBandsAtChristmas |  | Thank you image | those who've supported
8.12.21 | Our top fundraisers are xxx – well done! We're so grateful for all your fundraising efforts. Keep going! #BrassBandsAtChristmas | Add link to fundraiser page | Image of fundraising activity | tag fundraisers
9.12.21 | Show that special someone that you care. Purchase this xxxxx reward for them for an extra special treat. Help us spread the joy of #BrassBandsAtChristmas |  | Reward 1 | Target audience for reward
10.12.21 | Struggling for #gift ideas? Get your hands on xxxxx reward - available from our Crowdfunder page. #BrassBandsAtChristmas |  | Reward 2 | tag those who provided the reward
11.12.21 | Looking to bring in the New Year in a new and exciting way? Purchase our New Year #BrassBand Performance reward, available from our Crowdfunder page [URL] #BrassBandsAtChristmas |  | Reward 3 | tag those who provided the reward
12.12.21 | Check out this amazing reward [insert details]. You can buy it via our crowdfunder page and receive it by xxx date. All funds go to help #BrassBandsAtChristmas |  | Reward 4 | tag those who provided the reward
13.12.21 | Calling all LOCAL BUSINESSES! Please support #BrassBandsAtChristmas by donating here. Funds go towards saving your local brass band! All shares also greatly appreciated! |  | Campaign image | businesses
14.12.21 | The countdown to the end of our campaign has begun, but don't worry, if you still want to fundraise for us, you can! #BrassBandsAtChristmas |  | Fundraising image | contacts who've been sharing
15.12.21 | 5 days left! and only X% left till we reach our target! Click here to donate and help us get there! #BrassBandsAtChristmas |  | Countdown image | Local groups
16.12.21 | 4 days left! and only X% till we reach our target! Please help us get there. Click the link to support #BrassBandsAtChristmas |  | Countdown image | Crowdfunder (FB: @Crowdfunder, TW: @CrowdfunderUK)
17.12.21 | 3 days left on our #BrassBandsAtChristmas campaign! And only ...% till we reach our target! Let's go out on a high! |  | Countdown image | band members to share
18.12.21 | 2 days left! Will we reach our target? With your help we can do it! Please support us now [URL] #BrassBandsAtChristmas |  | Countdown image | key supporters
19.12.21 | The final day of our #BrassBandsAtChristmas campaign! Thanks to everyone who has pledged and fundraised for us so far. Click here [URL] to find out how much we've raised. #BrassBandsAtChristmas |  | Celebration image | all main supporters

## Email Example
EMAIL EXAMPLE
An example email to tweak and send out to your database/s when your individual Crowdfunder page is live (and once you’ve obtained some initial funding on it from your inner crowd)
Dear xx We’re so pleased to able to tell you about our new Crowdfunder campaign, where we’re aiming to raise [£XX] to help our band [do XXXX] By supporting our fundraiser, we can make sure that our Brass Band will continue to entertain our friends, family and the wider community in the years to come. Our crowdfunder is part of the #BrassBandsAtChristmas campaign, supported by Brass Bands England. You can help us raise our much-needed funds here: [your page URL] To achieve our £XX target, please can you: a. Donate whatever you can afford b. Select one of our fantastic rewards c. Create your own fundraising page and set yourself a fundraising challenge [insert example fundraising ideas] However you choose to support us, we’d really appreciate it if you could also share our campaign page widely with your network, via email, social media or tell them face to face. We've got some suggested wording for you to use below: “Please support our local Brass Band [name] by donating to their Crowdfunder: [insert URL] Brass bands are one of the essential parts of the Christmas experience (think carol concerts and Christmas shopping) and this project is part of a wider nationwide campaign to celebrate #BrassBandsAtChristmas.” We’d also be very grateful if you could forward this to any local businesses, celebrities, influencers, community groups or media outlets that you may know and ask them to support our campaign, either through donations, fundraising or by promoting it to their network. Many thanks again for your support.